## R&D Progress
Time | Overall Plan | Standard (Person in Charge: xxx) |  |  |  | Hero (Person in Charge: xxx) |  |  |  | Engineer (Person in Charge: xxx) |  |  |  | Sentry (Person in Charge: xxx)
|  | Mechanical | Electrical | Computer Vision | Progress | Mechanical | Electrical | Computer Vision | Others | Mechanical | Electrical | Computer Vision | Others | Mechanical | Electrical | Computer Vision | Others
Add other items as required
Feb. 19 - Feb. 23 |  | Objectives: 1. Complete chassis design - 1/2 Week Acceptance criteria: The chassis drawing passes the preliminary review of the mechanical group. The overall structural design meets requirements of key functions as expected. | Objectives: 1. Debug the basic functions of a gimbal - 1/3 Week Acceptance criteria: An environment is established for gimbal debugging. | Objectives: 1. Select the computing platform type - 1/1 Week Acceptance criteria: A type selection file is generated for forward design. | 1. Chassis design is postponed due to the following reason: (Reason why the acceptance criteria are not met)
Feb. 26 - Mar. 1 (Mid-Term Progress Assessment) |  | Objectives: 1. Complete chassis design - 2/2 Week Acceptance criteria: The chassis drawing passes the final review of the standard robot group. The structural design meets requirements of all functions as expected.
Mar. 4 - Mar. 8
Mar. 11 - Mar. 15
Mar. 18 - Mar. 22
Mar. 25 - Mar. 29
Apr. 1 - Apr. 5 (Final Robot Assessment)
Apr. 8 - Apr. 12
Apr. 15 - Apr. 19
Apr. 22 - Apr. 26
Add other items as required
Note 1: Mid-term progress assessment and final robot assessment are the milestones of the preparation stage. The season plan must specify the requirement of including the relevant progress in the mid-term progress assessment and final robot assessment reports for a closed loop of the season plan.
Note 2: Specific and measurable acceptance criteria must be set for the objectives.

## Operation Progress
Time | Overall Plan | Publicity |  | Sponsorship |  | Others
|  | Time Plan | Progress | Time Plan | Progress | Time Plan | Progress
Add other items as required
Feb. 19 - Feb. 23 |  | Objectives: 1. Complete the material collection for the WeChat article "Team Member Introduction - Mechanical" Acceptance criteria: Information of and at least one event related to each member of the mechanical group are collected.
Feb. 26 - Mar. 1 (Mid-Term Progress Assessment) |  | Objectives: 1. Complete the writing of the WeChat article "Team Member Introduction - Mechanical" Acceptance criteria: The WeChat article can be released at any time.
Mar. 4 - Mar. 8
Mar. 11 - Mar. 15
Mar. 18 - Mar. 22
Mar. 25 - Mar. 29
Apr. 1 - Apr. 5 (Final Robot Assessment)
Apr. 8 - Apr. 12
Apr. 15 - Apr. 19
Apr. 22 - Apr. 26
Add other items as required
Note 1: Mid-term progress assessment and final robot assessment are the milestones of the preparation stage. The season plan must specify the requirement of including the relevant progress in the mid-term progress assessment and final robot assessment reports for a closed loop of the season plan.
Note 2: Specific and measurable acceptance criteria must be set for the objectives.