## Gap Analysis
Meeting Minutes: In-competition Gap Analysis |  |  | Planned Manpower | Actual Manpower | Latest Progress | Original Plan | Any Differences from the Original Plan? | Difference | Area | Cause | Solution | Owner
R&D Progress | Standard | Mechanical | 3 | 2 | The first version of the Standard has been assembled and is ready for robot testing. | The first version of the Standard has been tested and is ready to enter the stage. | Yes | 1. The idler wheel chassis's stiffness is not up to the standard and failed the crash and drop test. 2. xxx | 1. Chassis structure design issues 2. xxx | 1. Design flaws: The key points bearing force were not simulated in the early stage of chassis design, resulting in chassis design problems and delays in development progress. 2. xxx | 1. Short-term plan: xxx Long-term plan: xxx | xxx
Electrical
Computer Vision
| Hero | Mechanical
Electrical
Computer Vision
| Engineer | Mechanical
Electrical
Computer Vision
| Sentry | Mechanical
Electrical
Computer Vision
Operation Progress | / | Sponsorship
| / | Marketing
Note 1: Mid-term progress assessment and final robot assessment are the milestones of the preparation stage. The season plan must specify the relevant progress in the mid-term progress assessment and final robot assessment reports to provide comprehensive information.
Note 2: Specific and measurable acceptance criteria must be set for the objectives.
Note on D1: double huang: Provide a manpower plan (the number of people and time planned to be allocated for each module)
Note on E1: double huang: Provide the actual manpower plan (the number of people and time actually allocated for each module)
Note on D2: double huang: Provide the number of people as originally planned. Enter 3 if 3 persons are planned.
Note on E2: double huang: Provide the number of people actually deployed. Enter 2 if 2 persons are deployed.
Note on F2: Author: Provide a concise description of the item and the expected result.
Note on H2: Author: The discrepancy between the planned and actual result: "Yes/No"
Note on I2: double huang: Conducting gap analysis on the delayed items is important, so is checking whether more or fewer tasks are accomplished.
Note on J2: double huang: Identify the problem based on the difference.
Note on K2: Author: Reflect on the problem and analyze the reasons why your plans are not completed.
Note on L2: Author: Based on the actual situation, identify a solution to the issue of not meeting expectations. Identify the root cause of the issue and develop long-term solutions applicable to similar problems. Avoid focusing solely on short-term, temporary solutions.
Note on M2: Author: Identify the individual responsible for implementing subsequent solutions.

## R&D Plan (Mid-term Updates)
Time | Overall Plan |  | Standard (Owner: xxx) | [6 empty] | Hero (Owner: xxx) | [7 empty] | Engineer (Owner: xxx) | [7 empty] | Sentry (Owner: xxx)
|  |  | Mechanical |  | Electrical |  | Computer Vision |  | Progress in Implementing the New Plan | Mechanical |  | Electrical |  | Computer Vision |  | Others |  | Mechanical |  | Electrical |  | Computer Vision |  | Others |  | Mechanical |  | Electrical |  | Computer Vision |  | Others
| Original Plan | New Plan (mid-term update) | Original Plan | New Plan (mid-term update) | Original Plan | New Plan (mid-term update) | Original Plan | New Plan (mid-term update) |  | Original Plan | New Plan (mid-term update) | Original Plan | New Plan (mid-term update) | Original Plan | New Plan (mid-term update) | Original Plan | New Plan (mid-term update) | Original Plan | New Plan (mid-term update) | Original Plan | New Plan (mid-term update) | Original Plan | New Plan (mid-term update) | Original Plan | New Plan (mid-term update) | Original Plan | New Plan (mid-term update) | Original Plan | New Plan (mid-term update) | Original Plan | New Plan (mid-term update) | Original Plan | New Plan (mid-term update)
Feb. 19 - Feb. 23 |  |  | Objectives: 1. Complete chassis design - 1/2 week Acceptance criteria: The chassis drawing passes the preliminary review of the mechanical team. The overall structural design meets the expectations for key functions. |  | Objectives: 1. Debug the basic functions of a gimbal - 1/3 week Acceptance criteria: An environment is established for gimbal debugging. |  | Objectives: 1. Select the computing platform type - 1/1 week Acceptance criteria: A type selection file is generated for forward design. |  | 1. Chassis design is postponed due to the following reason: (Reason why the acceptance criteria are not met)
Feb. 26 - Mar. 1 (Mid-Term Progress Assessment) |  |  | Objectives: 1. Complete chassis design - 2/2 week Acceptance criteria: The chassis drawing passes the final review of the standard robot team. The structural design meets the expectations for all functions.
Mar. 4 - Mar. 8
Mar. 11 - Mar. 15
Mar. 18 - Mar. 22
Mar. 25 - Mar. 29
April 1 - April 5 (Final Robot Assessment)
April 8 - April 12
April 15 - April 19
April 22 - April 26
Add information as needed
Note 1: Mid-term progress assessment and final robot assessment are the milestones of the preparation stage. The season plan must specify the relevant progress in the mid-term progress assessment and final robot assessment reports to provide comprehensive information.
Note 2: Specific and measurable acceptance criteria must be set for the objectives.

## Ops Plan (Mid-term Updates)
Time | Overall Plan |  | Marketing |  |  | Sponsorship |  |  | Others
| Original Plan | New Plan (mid-term update) | Original Plan | New Plan (mid-term update) | Progress in Implementing the New Plan | Original Plan | New Plan (mid-term update) | Progress in Implementing the New Plan | Original Plan | New Plan (mid-term update) | Progress in Implementing the New Plan
Feb. 19 - Feb. 23 |  |  | Objectives: 1. Complete the material collection for the WeChat article "Team Member Introduction - Mechanical" Acceptance criteria: Information about and at least one event related to each member of the mechanical team are collected.
Feb. 26 - Mar. 1 (Mid-Term Progress Assessment) |  |  | Objectives: 1. Complete the WeChat article "Team Member Introduction - Mechanical" Acceptance criteria: The WeChat article can be released at any time.
Mar. 4 - Mar. 8
Mar. 11 - Mar. 15
Mar. 18 - Mar. 22
Mar. 25 - Mar. 29
April 1 - April 5 (Final Robot Assessment)
April 8 - April 12
April 15 - April 19
April 22 - April 26
Add information as needed
Note 1: Mid-term progress assessment and final robot assessment are the milestones of the preparation stage. The season plan must specify the relevant progress in the mid-term progress assessment and final robot assessment reports to provide comprehensive information.
Note 2: Specific and measurable acceptance criteria must be set for the objectives.